## Sheet1
[5 empty] | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October
Activity | Person Responsible | Start Date | 17th - 21st | 24th - 28th | 31st - 4th | 7th - 11th | 14th - 18th | 21st - 25th | 28th - 2nd | 5th - 9th | 12th - 16th | 19th - 23rd | 26th - 30th | 2nd - 6th | 9th - 13th | 16th - 20th | 23rd - 27th | 30th - 3rd | 6th - 10th | 13th - 17th | 20th - 24th | 27th - 1st
Get further quotes for window replacement | ST | 2021-05-16
Order Windows | Contractor | 2021-06-29
Painting outside of toilet block | Graham Bradley | 2021-05-23
Order Information Boards | ST | 2021-05-16
Order Picnic Benches | ST | 2021-05-16
Order new entry and machine signage | ST | 2021-06-07
Receive Flowbird Quote | ST | 2021-05-09
Receive quotes for resurfacing | ST | 2021-05-09
Submit OZEV Grant Application | ST | 2021-05-16
Order resurfacing | ST | 2021-05-16
Install New benches |  | 2021-06-01
Install new information boards | Matt Kaunz | 2021-06-21
Install new ticket mchine | Flowbird | 2021-06-07
Receive response from OZEV | ST | 2021-06-28
Order Flowbird EV Chargers | ST | 2021-07-05
Install new surfaces |  | 2021-06-28
Install new windows | Graham Bradley | 2021-08-10
Wall and Fence Construction (Recycling) |  | 2021-07-12
Installation of Flowbird EV Chargers | Flowbird | 2021-08-30
Re-painting of road markings | YDNPA
Delineation of Parking Bays | ST
Wildflower Area | School/WI